## Plot
SL NO | District | MOUZA | Tahasil | Thana no | RI CIRCLE | KHATA NO | Kissam | Name of ROR | PLOT NO | TOTAL AREA (in Acres) | PROPOSED AREA (in Acres) | TOTAL AREA (in Hectares) | PROPOSED AREA (in Hectares) | LEASE CASE NO | Present Status | UA /IDCO to Tahasildar | Case details/ De - reservation Req. | Action to be taken | RI Report (1) | Proclamation | Objection Received | Others | Modification/Revision | Mising Case Prep./ DR Case. Prep. | Mising Case Prep./ DR Case. Prep. Number | Reason for Misc/DR case | Tree Enumeration | Order Sheet Prep. | Lease to IDCO | Lease to UA | Remarks
786 | Angul | Porapara Jungle | Chendipada | 41 | chendipada | 110 | Gochar | Rakhita | 173 | 0.14346 | 0.14346 | 0.3545 | 0.3545 | 101/2001 | Demand raised | no | request for allotment of land for setting up | serving notice for lapsing reservation | not started | no | no |  | no | no |  |  | not started | not started | no | no
787 | Angul | Porapara Jungle | Chendipada | 41 | chendipada | 110 | Gochar | Rakhita | 174 | 0.44759 | 0.44759 | 1.106 | 1.106 | 101/2001 | Demand raised | yes | request for allotment of land for setting up | serving notice for lapsing reservation | not started | yes | yes |  | yes | yes |  |  | not started | not started | yes | yes
788 | Angul | Porapara Jungle | Chendipada | 41 | chendipada | 110 | Gochar | Rakhita | 179 | 1.3395 | 1.3395 | 3.31 | 3.31 | 101/2001 | Demand raised | no | request for allotment of land for setting up | serving notice for lapsing reservation | complete | no | no |  | no | no |  |  | complete | complete | no | no
789 | Angul | Porapara Jungle | Chendipada | 41 | chendipada | 110 | Gochar | Rakhita | 182 | 0.027317 | 0.027317 | 0.0675 | 0.0675 | 101/2001 | Demand raised | no | request for allotment of land for setting up | serving notice for lapsing reservation | not started | no | no |  | no | no |  |  | not started | not started | no | no
839 | Angul | Porapara Jungle | Chendipada | 41 | chendipada | 110 | Gochar | Rakhita | 800 | 0.11696 | 0.11696 | 0.289 | 0.289 | 101/2001 | Demand raised | no | request for allotment of land for setting up | serving notice for lapsing reservation | complete | no | no |  | no | no |  |  | complete | complete | no | no
840 | Angul | Porapara Jungle | Chendipada | 41 | chendipada | 110 | Gochar | Rakhita | 809 | 0.1724 | 0.1724 | 0.426 | 0.426 | 101/2001 | Demand raised | no | request for allotment of land for setting up | serving notice for lapsing reservation | In progress | no | no |  | no | no |  |  | In progress | In progress | no | no
841 | Angul | Porapara Jungle | Chendipada | 41 | chendipada | 110 | Gochar | Rakhita | 816 | 0.012546 | 0.012546 | 0.031 | 0.031 | 101/2001 | Demand raised | yes | request for allotment of land for setting up | serving notice for lapsing reservation | In progress | yes | yes |  | yes | yes |  |  | In progress | In progress | yes | yes