## Plot
| LD01 | LD02 | LD03 | LD04 | LD05 | LD06 | LD07 | LD08 | LD09 | LA01 | LA02 | LA03 | LA04 | CD01 | CD02 | CD03 | CD04 | CD05 | CD06 | CD07 | CD08 | CD09 | CD10 | CD11 | CD12 | CD13 | CR01 | CR02 | CR03 | CR04 | CR05
SL NO | District | MOUZA | Tahasil | Thana no | RI CIRCLE | KHATA NO | Kissam | Name of ROR | PLOT NO | TOTAL AREA (in Acres) | PROPOSED AREA (in Acres) | TOTAL AREA (in Hectares) | PROPOSED AREA (in Hectares) | LEASE CASE NO | Present Status | UA /IDCO to Tahasildar | case details/de-reservation req. | Action to be taken | RI Report (1) | Proclamation | Objection Received | Others | Modification/Revision | Mising Case Prep./ DR Case. Prep. | Missing Case Prep./DR Case Number | Reason for Misc/DR case | Tree Enumeration | Order Sheet Prep. | Lease to IDCO | Lease to UA | Remarks
1 | Angul | Chhendipada Jungle | Chhendipada | 75 | chhendipada | 1006 | Nayanjori | Rakhita | 1378 | 0.18009 | 0.17815 | 0.445 | 0.4402 | 56/2002 | Lease Case to sub collector | yes | request for allotment of land for setting up | serving notice for lapsing reservation | In progress | yes | yes |  | yes | yes | 123 | dispute regarding ownership betwwen private parties & govt. land | In progress | In progress | yes | yes | lack of proper notice

## Summary of column codes
column codes | Code Details | Column Name
LD01 | Land Details | District
LD02 | Land Details | Village
LD03 | Land Details | Tahasil
LD04 | Land Details | Thana no
LD05 | Land Details | RI CIRCLE
LD06 | Land Details | KHATA NO
LD07 | Land Details | Kissam
LD08 | Land Details | Name of ROR
LD09 | Land Details | PLOT NO
LA01 | Land Area Details | TOTAL AREA (in Acres)
LA02 | Land Area Details | PROPOSED AREA (in Acres)
LA03 | Land Area Details | TOTAL AREA (in Hectares)
LA04 | Land Area Details | PROPOSED AREA (in Hectares)
CD01 | Case Details | LEASE CASE NO
CD02 | Case Details | Present Status
CD03 | Case Details | User Agency /IDCO to Tahasildar
CD04 | Case Details | Case details/de-reservation requisition
CD05 | Case Details | Action to be taken
CD06 | Case Details | RI Report (1)
CD07 | Case Details | Proclamation
CD08 | Case Details | Objection Received
CD09 | Case Details | Others
CD10 | Case Details | Modification/Revision
CD11 | Case Details | Mising Case Preparation/ DR Case. Preparation
CD12 | Case Details | Missing Case Prep./DR Case Number
CD13 | Case Details | Reason for Misc/DR case
CR01 | Case Record | Tree Enumeration
CR02 | Case Record | Order Sheet Preparation
CR03 | Case Record | Lease to IDCO
CR04 | Case Record | Lease to User Agency
CR05 | Case Record | Remarks